## Agile Roadmap Sprints 1-5
SCAPE APP - AGILE ROADMAP SPRINT roadmaps (SPRINTS 1-5)
Sprint Cycle | Task ID | Task Name | Functional Description | Feature Area | Priority | Owner | Status | Effort (SP)
Sprint 1: Core Foundation & UI/UX Design | TSK-1.1 | Brand Styling & Mood Board | Create a calming, experience-driven design system with HSL greens/blues, glassmorphism templates, and modern fonts. | Design | High | Kezia | Completed | 3
Sprint 1: Core Foundation & UI/UX Design | TSK-1.2 | Project Repository Setup | Setup Next.js workspace in TypeScript, configure Prisma schema, and install styling engines and packages. | Engineering | High | Palden | Completed | 2
Sprint 1: Core Foundation & UI/UX Design | TSK-1.3 | Responsive Home Screen Page | Build main landing page incorporating visual glassmorphism blocks, hero search inputs, and a beautifully blurred background. | Engineering | Medium | Palden | Completed | 5
Sprint 1: Core Foundation & UI/UX Design | TSK-1.4 | Unified Glassmorphic Header | Implement header routing containing links for Explore, Favorites, Blogs, and a placeholder Sign Out block. | Engineering | Medium | Kezia | Completed | 2
Sprint 2: Map Integration & Explore Spot Sidebar | TSK-2.1 | Maplibre GL Map Setup | Integrate Maplibre GL web container, center on Sydney, and establish boundary outskirts. | Engineering | High | Palden | Completed | 5
Sprint 2: Map Integration & Explore Spot Sidebar | TSK-2.2 | Sidebar Curated Spots Layout | Design sidebar listing cards including Bondi, Royal National Park, Manly, and Centennial Park with mini screenshots. | Engineering | High | Palden | Completed | 3
Sprint 2: Map Integration & Explore Spot Sidebar | TSK-2.3 | Interactive Pin Synchronization | Connect sidebar click triggers with map marker rendering, updating pins in real-time on selection. | Engineering | High | Palden | Completed | 5
Sprint 2: Map Integration & Explore Spot Sidebar | TSK-2.4 | Keyword & Search Filter Logic | Implement keyword-matching in backend database to instantly filter sidebar listings by user input. | Engineering | Medium | Palden | Completed | 3
Sprint 3: Saved Escapes (Favorites) & Blogs Platform | TSK-3.1 | Favorites Schema & Sync API | Construct Favorite schema in Prisma, setting up unique primary relations between users and saved locations. | Database | High | Palden | Completed | 3
Sprint 3: Saved Escapes (Favorites) & Blogs Platform | TSK-3.2 | Translucent Saved Escapes page | Build Favorites tab using glassmorphism layouts, displaying saved spots or elegant heart empty states. | Engineering | Medium | Kezia | Completed | 3
Sprint 3: Saved Escapes (Favorites) & Blogs Platform | TSK-3.3 | Blogs & Stories Grid Page | Implement community blogs layout structured as grids with cover photos, publication dates, and author metadata. | Engineering | Medium | Palden | Completed | 4
Sprint 3: Saved Escapes (Favorites) & Blogs Platform | TSK-3.4 | Blog Upload API Route | Develop API endpoint supporting photo files uploads and inserting posts records linked to user profiles. | Engineering | High | Palden | Completed | 5
Sprint 4: Secure Authentication & Password Recovery | TSK-4.1 | Prisma Database User Schema | Integrate User schema into Prisma file, migrating SQLite/MySQL profiles columns. | Database | High | Palden | Completed | 2
Sprint 4: Secure Authentication & Password Recovery | TSK-4.2 | Sleek Frosted-Glass Login Screen | Develop 'Welcome Back' auth page incorporating modern login credentials verification form. | Engineering | High | Kezia | Completed | 3
Sprint 4: Secure Authentication & Password Recovery | TSK-4.3 | Forgot Password Recovery Page | Build beautiful password recovery flow, allowing users to securely reset their credentials. | Engineering | Medium | Palden | Completed | 3
Sprint 4: Secure Authentication & Password Recovery | TSK-4.4 | JWT Session Cookies & Protected Routes | Implement secure JWT cookies auth token issuing on successful logins, blocking guest access on Favorites. | Engineering | High | Palden | Completed | 4
Sprint 5: System Testing, Polishing, and Launch | TSK-5.1 | Cross-Device Responsiveness Review | Test layout scaling on diverse tablet and mobile devices, fixing overlapping texts and maps. | QA / Testing | High | Kezia | In Progress | 3
Sprint 5: System Testing, Polishing, and Launch | TSK-5.2 | API Endpoints & Integration Tests | Conduct stress-tests on image upload API routes, verifying database relations are clean. | QA / Testing | Medium | Palden | In Progress | 3
Sprint 5: System Testing, Polishing, and Launch | TSK-5.3 | Asset & CSS Performance Optimization | Compress heavy background images, optimize Maplibre rendering speeds, and minimize bundle sizes. | Engineering | Medium | Kezia | In Progress | 2
Sprint 5: System Testing, Polishing, and Launch | TSK-5.4 | Production Server Deployment | Set environmental configs, complete dev.db migrations, and run final production build server. | DevOps | High | Palden | Not Started | 4
TOTAL ESTIMATED EFFORT | [7 empty] | 67
Team Members
Palden Gurung
Kezia Poudel